## Product Backlog
Product Backlog Id | Priority | User Story Id | User Story | Scrum Team Assigned | Status | Remark
1 | high | user001 | user registration | Amith | completed
2 | high | user002 | user login | Amey | completed
3 | low | user003 | movie browsing | Likitha | completed
4 | high | user004 | ticket booking | Ashish | completed
5 | low | user005 | movie review | Geetha | Progress
6 | medium | user006 | language update | Amith | progress
7 | high | user007 | seat selection | Amey | progress
8 | high | user008 | location | Amey | completed
9 | high | user009 | payment | Sairam | completed
10 | medium | user010 | movie rating | Anuj | progress
11 | high | user011 | notification | Ankit | completed
12 | low | user012 | food | Vinay | progress
13 | medium | user013 | other activities | Ankit | progress
14 | high | user014 | feedback | Vinay | completed
15 | high | user015 | movie listing | Ashish | Completed
16 | medium | user016 | receive movie reminders | Anuj | progress

## Sprint Backlog 1
USER STORY ID | USER STORY NAME | USER STORY STEP DEFINITION | Acceptance Criteria | ASSIGNED TO | ESTIMATION | STATUS | REMARKS
user001 | User registration | As a user I can provide my email id, phone no., password, username, gender, DOB for registration | Enter valid email id, phone no, password, username , DOB | Amit | 5 hrs | completed
Verify the email and phone no. using OTP
After successful registration as a user I am navigated to the home screen
user002 | Login | As a registered user I can able to login into system | Enter valid username, password | Amey | 6 hrs | completed
As a registered user I can login and see the list of movies
user003 | Movie browsing | As a user I can browse movies by title,genere,release date.So that I can easily find the movie |  | Likhitha | 8 hrs | completed
As a user I can browse recent movies.
user015 | movie listing | As a admin I can add the movies |  | Ashish | 3hrs | completed
As an admin I can remove shows

## Sprint Backlog 2
USER STORY ID | USER STORY NAME | USER STORY STEP DEFINITION | Acceptance Criteria | ASSIGNED TO | ESTIMATION | STATUS
user008 | location | As a user I can provide my location | Enter valid location of a city | Amey | 2hr | completed
user004 | ticket booking | As a user I can search the movie name from the search bar | The user should be shown appropriate results | Ashish | 8hr | completed
|  | After successfully selecting the movie the user is directed to seat selection | The user should navigated to the seat selection page
user007 | seat selection | As a user i can select the seat no through selecting section |  | Amey | 10hr | progress
|  | As a user after selecting the seats and showtime I am navigated to payment page | The user should navigated to the payment page
user009 | payment | As a user i can do the payment | Enter valid payment method and do the payment | Sairam | 8hr
As a user after successful payment my show will be successfully booked
user011 | notification | As the user can be notify for the show timing and new released movies | user should route on track page after clicking on notification | Ankit | 4hr | completed
As user can track show

## Sprint Backlog 3
USER STORY ID | USER STORY NAME | USER STORY STEP DEFINITION | Acceptance Criteria | ASSIGNED TO | ESTIMATION | STATUS
user005 | movie review | As a Registered user I can able to review particular movie |  | Geetha | 4 Hours | Progress
user010 | movie rating | As the user I want to rate and review movies I have watched |  | Anuj | 5hr | progress
user012 | food | As the user I can enjoy the food in between | Show avilable food items | Vinay |  | progress
As a admin I can add the food items
user013 | other activites | As in interval time you can enjoy games section too | Shows games available | Ankit | 4hr | Progress
user016 | Receive Movie Reminders | As a user I want to receive reminders about my upcoming movie showtime |  | Anuj | 4hr | progress
user006 | language update | As a user language should automatically set to the language of my device | Set default langauage | Amit | 1hr | progress
As a user I can set a preffered language

## Kanban
TODO | In Progress |  |  |  |  | Completed
| Plan | Design | Develop | Test | Deploy
user registration | done | done | done | done | done | completed
user login | done | done | done | done | done | completed
movie browsing | done | done | done | done | done | completed
ticket booking | done | done | done | done | done | completed
movie review | done | done | done
language update | done | done
seat selection | done | done | done
location | done | done | done | done | done | completed
payment | done | done | done | done | done | completed
movie rating | done | done | done
notification | done | done | done | done | done | completed
food | done | done
other activities | done | done | done
feedback | done | done | done | done | done | completed
movie listing | done | done | done | done | done | completed
receive movie reminders | done | done

## Defect Tracking
defect id | defect | created on | creater | assigned to | severity | priority | status
d001 | User is not able to enter their name in the registration screen | 2024-06-20 | Ashish | Anuj | high | high | open
d002 | Movie List not updating on date and time | 2024-06-20 | Ankit | Likhitha | high | high | open
d003 | User is not able to pay with the debit card | 2024-06-19 | Sairam | Sairam | medium | medium | close
d004 | User cannot select seats during booking | 2024-06-22 | Geetha | Amey | medium | medium | close